## Sprint5
Capacity, Committed, Effort, and Delivered Metric
Sprint: | 5
Team: | Team Eric's Angels
Scrum Master: | Matthew O'Malley
Product Owner | Connor Thompson
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Matthew O'Malley | 14 | 13 | 13 | 13 | 92.86% | 100% | 92.86%
Connor Thompson | 14 | 12 | 12 | 9 | 85.71% | 75% | 64.29%
Vincent Cortesi | 14 | 12 | 12 | 9 | 85.71% | 75% | 64.29%
Team Totals: | 42 | 37 | 37 | 31 | 88.1% | 83.78% | 73.81%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | CT |  | March 26, 2023 @ 2:04 PM
Scrum Master | MO |  | March 26, 2023 @ 4:00 PM
Final Signoff | Initial |  | Date
Product Owner
Scrum Master

## Sprint6
Capacity, Committed, Effort, and Delivered Metric
Sprint: | 6
Team: | Team Eric's Angels
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Matthew O'Malley | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Connor Thompson | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Vincent Cortesi | 1 | 1 | 1 | 1 | 100% | 100% | 100%
#REF! | 1 | 1 | 1 | 1 | 100% | 100% | 100%
#REF! | 1 | 1 | 1 | 1 | 100% | 100% | 100%
#REF! | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Totals: | 6 | 6 | 6 | 6 | 100% | 100% | 100%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm

## Sprint7
Capacity, Committed, Effort, and Delivered Metric
Sprint: | 7
Team: | Team Eric's Angels
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Matthew O'Malley | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Connor Thompson | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Vincent Cortesi | 1 | 1 | 1 | 1 | 100% | 100% | 100%
#REF! | 1 | 1 | 1 | 1 | 100% | 100% | 100%
#REF! | 1 | 1 | 1 | 1 | 100% | 100% | 100%
#REF! | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Totals: | 6 | 6 | 6 | 6 | 100% | 100% | 100%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm

## Sprint8
Capacity, Committed, Effort, and Delivered Metric
Sprint: | 8
Team: | Team Eric's Angels
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Matthew O'Malley | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Connor Thompson | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Vincent Cortesi | 1 | 1 | 1 | 1 | 100% | 100% | 100%
#REF! | 1 | 1 | 1 | 1 | 100% | 100% | 100%
#REF! | 1 | 1 | 1 | 1 | 100% | 100% | 100%
#REF! | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Totals: | 6 | 6 | 6 | 6 | 100% | 100% | 100%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm